## project
Task ID | Task Name | Start Date | Priority | Status | Notes | Completion% | Due Date | Duration
1 | Write Repot | 2024-01-10 | High | Not started | Research complete | 0% | 2024-01-19 | 9
2 | Email Clients | 2024-01-12 | Medium | In progress | Drafting emails | 40% | 2024-02-10 | 29
3 | Update Website | 2024-01-15 | High | Not started | Needs content | 0% | 2024-01-28 | 13
4 | Schedule Meeting | 2024-01-11 | Low | Completed | Sent invites | 100% | 2024-03-04 | 53
5 | Update Software | 2024-01-14 | High | In progress | Waiting for approval | 60% | 2024-01-20 | 6
6 | Call Client A | 2024-01-11 | Medium | Completed | Project disscused | 100% | 2024-02-02 | 22
7 | prepare Presentation | 2024-01-15 | High | Not started | Need to gather data | 0% | 2024-01-25 | 10
8 | Design logo for website | 2024-01-13 | Low | Not started | Initial ideas | 0% | 2024-03-13 | 60
9 | Book conference ticket | 2024-01-18 | Medium | In progress | Looking for documents | 50% | 2024-02-28 | 41
10 | Submit tax documents | 2024-01-20 | High | Not started | Deadline approaching | 0% | 2024-01-30 | 10
11 | Organize meeting room | 2024-01-12 | Low | Completed | Reserved the room | 100% | 2024-03-22 | 70
12 | Buy office supplies | 2024-01-16 | Low | Not started | Check inventory | 0% | 2024-03-28 | 72
13 | Clean the workspace | 2024-01-14 | Low | In progress | Organizing files | 40% | 2024-03-22 | 68
14 | Prepare invoice | 2024-01-17 | Medium | Completed | Sent to client B | 100% | 2024-02-17 | 31
15 | Research competitors | 2024-01-13 | Medium | Not started | Need market analysis | 0% | 2024-02-13 | 31
16 | Update social media | 2024-01-11 | High | Completed | Posted new updates | 100% | 2024-02-01 | 21
17 | write blog post | 2024-01-19 | Low | Not started | Decide on topic | 0% | 2024-02-19 | 31
18 | Review financial statements | 2024-01-15 | High | In progress | Need accounting data | 80% | 2024-01-25 | 10
19 | Clean mail box | 2024-01-13 | Low | Completed | Deleted old emails | 100% | 2024-03-13 | 60
20 | Send newsletters | 2024-01-16 | Medium | In progress | Writing content | 30% | 2024-02-05 | 20
21 | Confirm event venue | 2024-01-14 | High | Not started | Need to call venue | 0% | 2024-01-24 | 10
22 | Prepare meeting agenda | 2024-01-12 | Medium | Completed | Agenda shared with team | 100% | 2024-01-30 | 18
23 | Set up project plan | 2024-01-17 | High | Not started | Need approval | 0% | 2024-01-27 | 10
24 | Test product features | 2024-01-18 | Medium | In progress | Testing new updated | 50% | 2024-02-01 | 14
25 | Analyze customer feedback | 2024-01-19 | Medium | In progress | Collect data | 0% | 2024-02-19 | 31
26 | Schedule team call | 2024-01-20 | Low | Completed | Call scheduled | 100% | 2024-02-19 | 30
27 | Follow up with supplier | 2024-01-16 | Medium | In progress | waiting for response | 20% | 2024-02-18 | 33
28 | Design business card | 2024-01-13 | Low | Completed | Need new design | 100% | 2024-02-23 | 41
29 | Update project timeline | 2024-01-14 | High | In progress | Review task duration | 20% | 2024-01-29 | 15
30 | Contact HR | 2024-01-15 | Medium | Not started | Discuss benefits | 0% | 2024-02-22 | 38
SUMMARY
| Total task | 30
| Task completed | 9
| Total work in progress | 10
| Total task not started | 11
| High | 10
| Low | 9
| Medium | 11
|  | Status | (All)
|  | Row Labels | Sum of Completion%
|  | Analyze customer feedback | 0%
|  | Book conference ticket | 50%
|  | Buy office supplies | 0%
|  | Call Client A | 100%
|  | Clean mail box | 100%
|  | Clean the workspace | 40%
|  | Confirm event venue | 0%
|  | Contact HR | 0%
|  | Design business card | 100%
|  | Design logo for website | 0%
|  | Email Clients | 40%
|  | Follow up with supplier | 20%
|  | Organize meeting room | 100%
|  | Prepare invoice | 100%
|  | Prepare meeting agenda | 100%
|  | prepare Presentation | 0%
|  | Research competitors | 0%
|  | Review financial statements | 80%
|  | Schedule Meeting | 100%
|  | Schedule team call | 100%
|  | Send newsletters | 30%
|  | Set up project plan | 0%
|  | Submit tax documents | 0%
|  | Test product features | 50%
|  | Update project timeline | 20%
|  | Update social media | 100%
|  | Update Software | 60%
|  | Update Website | 0%
|  | write blog post | 0%
|  | Write Repot | 0%
|  | Grand Total | 1290%